## Sheet1
Type | Description | Date of request | Who In charge | Action Closed | Status
ENH | Swap xyz pane with xy pane | Wish list wiki end of jan | Arnaud | done 3mar
ENH | Synchronize zoom and panning of xy, yz, and xz panes to each other | Wish list wiki end of jan | Arnaud | done 6mar
| Dragable and instantly refreshed reslice lines | Wish list wiki end of jan
| Some graphical display of transfer function appears while adjusting brightness/contrast with mouse (low priority) | Wish list wiki end of jan
| Some way to change transfer function for volume rendering | Wish list wiki end of jan
ENH | Make font for textual info bigger | Wish list wiki end of jan
ENH | Eliminate redundancy in textual info | Wish list wiki end of jan | Lydie
| Have widget to turn channels on and off and to apply different LUTs to each channel | Wish list wiki end of jan
FEA | Have widget to turn on/off actors (xy, yz, xz, volume, figures, meshes, tracks, lineages) | Wish list wiki end of jan
FEA | Display location in x,y,z,t for pixels (integers) and real world coordinates (microns) | Wish list wiki end of jan |  | done
FEA | Need views for xyz and xyt | Wish list wiki end of jan | Arnaud | done
| LSM files : |  | Alex
FEA | Read 2D, 3D, 2ch, 3ch |  | Alex | done 20mar
FEA | Write 1 ch |  | Alex | done 20mar
FEA | Write 3 ch |  | Alex | done 20mar
FEA | Integration Gofigure |  | Alex | done 20mar
ENH | Change the visible status of the buttons when full screen view selected | Meeting 24feb | Lydie | done 9mar
ENH | Memorize the layout ( panes settings ) for the file: recent open files | Meeting 24feb | Lydie
ENH | Put a filter for the type of files in the open menu (e.g. *.lsm, *.tiff, *.mha) for all supported files | Meeting 24feb | Lydie | done6apr
ENH | Shortcuts to handle for opening a file | Meeting 24feb | Lydie | done6apr
FEA | Make a splash screen appears when loading the application | Meeting 24feb | Lydie | done 11mar
FEA | Show progress bars for the loading of files | Meeting 24feb | Lydie |  | 1rst part: show a widget when loading data and close it when image loaded)
| Check the speed for loading the application/files | Meeting 24feb
ENH | Rotate the left below view | Meeting 24feb | Arnaud | done16mar
ENH | Change the S-D with I-V (Dorsal-ventral) | Meeting 24feb | Arnaud | done 27feb
ENH | Synchronization of the splitters | Meeting 24feb | Lydie | done 5mar
FEA | Button to hide/show the scales | Meeting 10mar | Lydie | done 11mar
FEA | Screenshot available only on full screen view | Meeting 10mar | Lydie | done 31mar09
ENH | Drag the splitters diagonaly | Meeting 10mar | arnaud
FEA | xyt | Meeting 10mar | alex
FEA | time vizu (able to change the quadview with a slider for the t dimension) | Meeting 10mar | alex | done
FEA | export results + movie | Meeting 10mar | alex
FEA | able to load JPEG with RGB values | Meeting 10mar | alex
FEA | volume rendering on/off integrated |  | Lydie | done 12mar
FEA | Open recent files |  | Lydie | done 12mar
ENH | No icon for "quit" in the toolbar | Meeting 24mar | Lydie | done 25mar
ENH | When moving the mouse wheel, the slider for the slices has to move also | Meeting 24mar | Arnaud | done
MySQL:
FEA | Vtk+MySql |  | Alex | done
FEA | Connection server |  | Alex | done
FEA | Print out DB |  | Alex | done
FEA | Print out tables |  | Alex | done | need to be integrated in Gofigure
FEA | Creation DB Gofigure |  | Alex | done
ENH | Splash screen too big on my laptop | email Sean 3apr09 | Lydie
FEA | serialize size/layout of windows | email Sean 3apr09 | Lydie |  | idem action 20 ? More explanation from Sean:Serialize size/layout of windows: When you close GOFigure, it should remember the size of the main window, position of main window, maximized vs. non-maximized, size/position of any child windows, position of splitter windows. Next time you open GoFigure it should return to these window states. In Windows you’d store this in the registry. Not sure how Qt deals with it, but Qt has this figured out for the Most Recently Used file list so perhaps it does for serializing windows also.
FEA | need icon for desktop shortcut/associated files | email Sean 3apr09 | Lydie
ENH | add scroll bars as in GF1 | email Sean 3apr09 | Lydie
ENH | on 3d view, add dashed line at intersection of each plane, The line should be the same color as the rectangle that it is coplanar with | email Sean 3apr09 | arnaud
| Data extraction: | Wish list Nick end of jan
| cell position (x,y,z) | Wish list Nick end of jan
| cell movement (direction, speed) | Wish list Nick end of jan
| cell size (nucleus, area enclosed by membrane) | Wish list Nick end of jan
| cell count/ density | Wish list Nick end of jan
| sum of brightness of cell area per channel (for expression quantitation) | Wish list Nick end of jan
| # cell divisions for the timepoint | Wish list Nick end of jan
| # cell deaths for the timepoint | Wish list Nick end of jan
| Visual aids/ Filters | Wish list Nick end of jan
| highlight dividing cells | Wish list Nick end of jan
| highlight new cells | Wish list Nick end of jan
| highlight occurrence of cell death | Wish list Nick end of jan
| overlays of several timepoints/ track movement | Wish list Nick end of jan
| show cell lineage, history (user can set # generations) | Wish list Nick end of jan
| highlight cells by user defined speed | Wish list Nick end of jan
| highlight cells by user defined density | Wish list Nick end of jan
| 3D reconstruction of one or several timepoints | Wish list Nick end of jan
| manual correction of segmentation/ tracking | Wish list Nick end of jan