## Sheet1
Type | Description | Date of request | Who In charge | Action Closed | date closed | duration | Status
ENH | Swap xyz pane with xy pane | 2009-01-01 | Arnaud | done | 2009-03-03 | 62
ENH | Synchronize zoom and panning of xy, yz, and xz panes to each other | 2009-01-01 | Arnaud | done | 2009-03-06 | 65
| Dragable and instantly refreshed reslice lines | 2009-01-01 |  |  | 2009-04-08 | 97
| Some graphical display of transfer function appears while adjusting brightness/contrast with mouse (low priority) | 2009-01-01 |  |  | 2009-04-08 | 97
| Some way to change transfer function for volume rendering | 2009-01-01 |  |  | 2009-04-08 | 97
ENH | Make font for textual info bigger | 2009-01-01 |  |  | 2009-04-08 | 97
ENH | Eliminate redundancy in textual info | 2009-01-01 | Lydie |  | 2009-04-08 | 97
| Have widget to turn channels on and off and to apply different LUTs to each channel | 2009-01-01 |  |  | 2009-04-08 | 97
FEA | Have widget to turn on/off actors (xy, yz, xz, volume, figures, meshes, tracks, lineages) | 2009-01-01 |  |  | 2009-04-08 | 97
FEA | Display location in x,y,z,t for pixels (integers) and real world coordinates (microns) | 2009-01-01 | Arnaud | done | 2009-03-01 | 60
FEA | Need views for xyz and xyt | 2009-01-01 | Arnaud | done | 2009-03-01 | 60
| LSM files : |  | Alex
FEA | Read 2D, 3D, 2ch, 3ch | 2009-01-01 | Alex | done | 2009-03-20 | 79
FEA | Write 1 ch | 2009-01-01 | Alex | done | 2009-03-20 | 79
FEA | Write 3 ch | 2009-01-01 | Alex | done | 2009-03-20 | 79
FEA | Integration Gofigure | 2009-01-01 | Alex | done | 2009-03-20 | 79
ENH | Change the visible status of the buttons when full screen view selected | 2009-02-24 | Lydie | done | 2009-03-20 | 26
ENH | Memorize the layout ( panes settings ) for the file: recent open files | 2009-02-24 | Lydie |  | 2009-04-08 | 44
ENH | Put a filter for the type of files in the open menu (e.g. *.lsm, *.tiff, *.mha) for all supported files | 2009-02-24 | Lydie | done | 2009-04-06 | 42
ENH | Shortcuts to handle for opening a file | 2009-02-24 | Lydie | done | 2009-04-06 | 42
FEA | Make a splash screen appears when loading the application | 2009-02-24 | Lydie | done | 2009-03-11 | 17
FEA | Show progress bars for the loading of files | 2009-02-24 | Lydie |  | 2009-04-08 | 44 | 1rst part: show a widget when loading data and close it when image loaded)
| Check the speed for loading the application/files | 2009-02-24 |  |  | 2009-04-08 | 44
ENH | Rotate the left below view | 2009-02-24 | Arnaud | done | 2009-03-16 | 22
ENH | Change the S-D with I-V (Dorsal-ventral) | 2009-02-24 | Arnaud | done | 2009-02-27 | 3
ENH | Synchronization of the splitters | 2009-02-24 | Lydie | done | 2009-03-05 | 11
FEA | Button to hide/show the scales | 2009-03-10 | Lydie | done | 2009-03-11 | 1
FEA | Screenshot available only on full screen view | 2009-03-10 | Lydie | done | 2009-03-31 | 21
ENH | Drag the splitters diagonaly | 2009-03-10 | arnaud |  | 2009-04-08 | 28
FEA | xyt | 2009-03-10 | alex |  | 2009-04-08 | 28
FEA | time vizu (able to change the quadview with a slider for the t dimension) | 2009-03-10 | alex | done | 2009-03-24 | 14
FEA | export results + movie | 2009-03-10 | alex |  | 2009-04-08 | 28
FEA | able to load JPEG with RGB values | 2009-03-10 | alex |  | 2009-04-08 | 28
FEA | volume rendering on/off integrated | 2009-03-12 | Lydie | done | 2009-03-12 | 0
FEA | Open recent files | 2009-03-12 | Lydie | done | 2009-03-12 | 0
ENH | No icon for "quit" in the toolbar | 2009-03-10 | Lydie | done | 2009-03-25 | 15
ENH | When moving the mouse wheel, the slider for the slices has to move also | 2009-03-24 | Arnaud | done | 2009-03-25 | 1
MySQL:
FEA | Vtk+MySql | 2009-01-01 | Alex | done | 2009-03-01 | 60
FEA | Connection server | 2009-01-01 | Alex | done | 2009-03-01 | 60
FEA | Print out DB | 2009-01-01 | Alex | done | 2009-03-01 | 60
FEA | Print out tables | 2009-01-01 | Alex | done | 2009-03-01 | 60 | need to be integrated in Gofigure
FEA | Creation DB Gofigure | 2009-01-01 | Alex | done | 2009-03-01 | 60
ENH | Splash screen too big on my laptop | 2009-04-03 | Lydie |  | 2009-04-08 | 5
FEA | serialize size/layout of windows | 2009-04-03 | Lydie |  | 2009-04-08 | 5 | idem action 20 ? More explanation from Sean:Serialize size/layout of windows: When you close GOFigure, it should remember the size of the main window, position of main window, maximized vs. non-maximized, size/position of any child windows, position of splitter windows. Next time you open GoFigure it should return to these window states. In Windows you’d store this in the registry. Not sure how Qt deals with it, but Qt has this figured out for the Most Recently Used file list so perhaps it does for serializing windows also.
FEA | need icon for desktop shortcut/associated files | 2009-04-03 | Lydie |  | 2009-04-08 | 5
ENH | add scroll bars as in GF1 | 2009-04-03 | Lydie |  | 2009-04-08 | 5
ENH | on 3d view, add dashed line at intersection of each plane, The line should be the same color as the rectangle that it is coplanar with | 2009-04-03 | arnaud |  | 2009-04-08 | 5
Data extraction:
| cell position (x,y,z) | 2009-01-01 |  |  | 2009-04-08 | 97
| cell movement (direction, speed) | 2009-01-01 |  |  | 2009-04-08 | 97
| cell size (nucleus, area enclosed by membrane) | 2009-01-01 |  |  | 2009-04-08 | 97
| cell count/ density | 2009-01-01 |  |  | 2009-04-08 | 97
| sum of brightness of cell area per channel (for expression quantitation) | 2009-01-01 |  |  | 2009-04-08 | 97
| # cell divisions for the timepoint | 2009-01-01 |  |  | 2009-04-08 | 97
| # cell deaths for the timepoint | 2009-01-01 |  |  | 2009-04-08 | 97
Visual aids/ Filters
| highlight dividing cells | 2009-01-01 |  |  | 2009-04-08 | 97
| highlight new cells | 2009-01-01 |  |  | 2009-04-08 | 97
| highlight occurrence of cell death | 2009-01-01 |  |  | 2009-04-08 | 97
| overlays of several timepoints/ track movement | 2009-01-01 |  |  | 2009-04-08 | 97
| show cell lineage, history (user can set # generations) | 2009-01-01 |  |  | 2009-04-08 | 97
| highlight cells by user defined speed | 2009-01-01 |  |  | 2009-04-08 | 97
| highlight cells by user defined density | 2009-01-01 |  |  | 2009-04-08 | 97
| 3D reconstruction of one or several timepoints | 2009-01-01 |  |  | 2009-04-08 | 97
| manual correction of segmentation/ tracking | 2009-01-01 |  |  | 2009-04-08 | 97